LOGICAL FRAMEWORK

| PROJECT DESCRIPTION | OBJECTIVELY VERIFIABLE INDICATORS | SOURCES OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- |
| Overall objective | Contribute to the enhancement of the quality of early childhood education and care | - | - | Children’s availability |
| Specific objective | Publish multilingual e-guidelines on media literacy in ECE through DST in 36 months | Multilingual e-guidelines uploaded | Project’s website | - |
| Results | IO1 – Draft of best practices of digital storytelling in early childhood in 6 months IO2 – Analyze scientifically the DST experimentation in the targeted kindergartens/schools in 24 months IO3 - Design a training reference framework for teachers for DST in early childhood education in 5 months IO 4 – Create and develop an online shared platform containing project’s resources, materials and documentation in 36 months IO 5 – Design a manual of best practices and case studies on the use of DST in early childhood in the involved kindergartens and schools in 21 months IO 6 - Draft multilingual e-guidelines on media literacy in ECE through DST in 35 months | Manual of best practices drafted by UNIMORE and shared with every partner Observation report drafted by JYU and shared with every partner Reference framework drafted by all partners and collected by CoopSelios Online shared platform created and developed by CL Manual of best practices and case studies designed and shared by MSGSU Multilingual e-guidelines on media literacy in ECE drafted by all partners and collected by CoopSelios | Email read receipt Email read receipt Email read receipt Project’s website Email read receipt Email read receipt | Information availability - Teachers’ availability - Teachers’ and children’s availability - |
| Activities | IM–A1 – Set up a steering committee within the first two months IM–A2 – Sign the partners’ agreement within the first month IM–A3 – Draft the working plan within the first two months IM–A4 – Project’s progress monitoring reports every six months IM–A5 – Set up the working groups within the first two months IM–A6.1 – Draft Q&E plan within the first 3 months IM–A6.2 – External evaluation for every single IO | Steering committee set up Agreement signed Working plan drafted and presented during the KOM by CoopSelios Monitoring reports analyzed by CS Working group set up during the KOM Q&E plan drafted by JYU IOs evaluated by the external evaluator | Kick off meeting report Direct observation Kick off meeting report Analysis report Kick off meeting report Direct observation Evaluation reports collected by CoopSelios | Members’ availability - - - - - - |
| PROJECT DESCRIPTION | OBJECTIVELY VERIFIABLE INDICATORS | SOURCES OF VERIFICATION | ASSUMPTIONS |
| Activities | IM–A7.1 – Draft a dissemination plan within the first 3 months IM–A7.1 – Submit the dissemination final report within month n° 36 IM–A8.1 – Set up the project’s web site within the first 4 months IM–A8.2 – Set up the project’s social network profiles within the first 5 months IM–A8.2 – Set up the project’s forum/blogs within the first 6 months IM–A9.1 – Draft the exploitation plan draft within the first 3 months IM–A9.2 – Draft the final exploitation report within month n° 36 IM–A10 – Draft the stakeholders’ map within 6 months IO1–A2 – Sign the agreement on the structure concept of manual of best practices of DST in EC within the first two months IO1–A2 – Share the “state of art” research results of every partner involved within the first 5 months IO2–A1 – Define the focuses of observation of scientific research within months n°9 IO2–A2 – Define methodology of observation of scientific research within months n°11 IO2–A3 – Define the schedule of observation of scientific research activities within months n°12 IO2–A4 – Survey the experimental activities made by every partner involved between month n°13 and month n°30 | Dissemination plan drafted by PH KA and shared with every partner Dissemination final report submitted to CoopSelios by PH KA Project’s web site set up by CL Project’s social network profiles set up by CL Project’s forum/blogs set up by CL Exploitation plan drafted by MSGSU and shared with every partner Final exploitation report drafted by MSGSU and shared with every partner Stakeholders’ map drafted by MSGSU and shared with every partner Structure concept of manual of best practices of DST in EC agreement signed by all partners during the KOM State of art research results collected by UNIMORE Focuses of observation of scientific research defined by JYU and shared with every partner Methodology of observation of scientific research defined by JYU and shared with every partner Schedule of observation of scientific research defined by every partner and collected by JYU Observation report and data collected sent to JYU by every partner | Email read receipt Email read receipt Online direct observation Online direct observation Online direct observation Email read receipt Email read receipt Email read receipt Kick off meeting report Email read receipt Email read receipt Email read receipt Email read receipt Email read receipt | - - - - - - - - Data availability - - - - - |

| PROJECT DESCRIPTION | OBJECTIVELY VERIFIABLE INDICATORS | SOURCES OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- |
| Activities | IO2–A5 – Analyze the experimental activities within month n°31 IO2–A6 – Draft the observation report within month n° 32 IO3–A1 – Define the competence requirements needed to attend the training for DST teachers within month n°7 IO3–A2 – Define the model/methodology/contents of training of DST teachers within month n°8 IO3–A3 – Design and produce the online training contents for DST teachers within month n°8 IO3–A4 – Deliver the training course and activities within month n° 11 IO4–A1 – Design the project’s online platform within month n°4 IO4–A2 – Develop and release the online platform within month n°12 IO4–A3 – Develop the multimedia training modules online pills within month n°8 IO4–A4 – Manage and update the project’s online platform during the entire project IO5–A1 – Plan the experimentation activities within month n°12 IO5–A2 – Experience the designed practices in at least three schools for each partner’s country between month n°13 and month n°30 IO5–A3 – Gather teachers’ information on experimentation activities within month n°31 IO5–A4 – Analyze the data on experimentation activities within month n°32 | Data analysis report drafted by JYU included in IO2-A6 Observation report drafted by JYU and shared with every partner List of competence requirements drafted by every partner and sent to CoopSelios Model/methodology/contents description drafted by every partner and sent to CoopSelios Online training and contents designed and produced by every partner and sent to CoopSelios Trained the number of teachers planned by every partner Online platform designed by CL Online platform developed and released by CL Online training contents uploaded on the projects online platform by CL Platform managed and updated by CL Experimentation activities planned by every partner and sent to CoopSelios Designed practices experienced by every partner Teachers’ information gathered by MSGSU from every partner involved Data on experimentation activities analyzed by MSGSU | Direct observation Email read receipt Email read receipt Email read receipt . Email read receipt Attendance sheets and tests’ results Direct observation Direct online observation Direct online observation Direct online observation Direct observation of the activities schedule Teachers’ experimentation report Email read receipt Best practices’/case studies’ report | - - - - - Teachers’ availability - - - - - Schools availability - - |
| PROJECT DESCRIPTION | OBJECTIVELY VERIFIABLE INDICATORS | SOURCES OF VERIFICATION | ASSUMPTIONS |
| Activities | IO6–A1 – Draft the concept of the guidelines within month n°32 IO6–A2 – Analyze and synthesize the documentation produced by IO5 within month n°34 IO6–A3 – Analyze and synthesize the documentation produced by IO2 within month n°34 IO6–A4 – Draft the guidelines on media literacy in ECE trough DST within month n° 35 | Concept guidelines drafted by CS and shared with every partner Documentation analyzed, synthesized by every partner and sent to CS Documentation analyzed, synthesized by every partner and sent to CS Guidelines on media literacy in ECE trough DST drafted by CS | Email read receipt Email read receipt Email read receipt Direct observation | - - - - |

CS  = CoopSelios (IT)

JYU = Jyväskylän Yliopisto University (FIN)

PH KA = Pädagogische Hochschule Karlsruhe (D)

MSGSU = Mimar Sinan Güzel Sanatlar Üniversitesi  (TR)

UNIMORE = Università di Modena e Reggio Emilia (IT)

CL = Computer Learning (IT)